## Sheet1
| Area | Project | Comment
1 | Doing | Cholesterol via GC/MS | Results not stable - to discuss with Trevor.
2 | Doing | Nominate C6 Preferred List | Circulated for comment.
3 | With Lab | ASE Trial Extractions | Waiting for filters
4 | With Lab | Bromide in Mercury Method | Lab trialling need for Br
5 | With Lab | CARN01 Validation Report | Waiting on bias data
6 | With Lab | FAME01 - Trialling KOH | In progress
7 | With Lab | Glycerol Bath | CAPEX done
8 | With Lab | MICP02 convert ICPM06 | IT issues??
9 | With Lab | Nitrogen By HACH | In progress
10 | With Lab | PVAL and Light Effects | Report created - no feedback yet.
11 | With Lab | RMDX using Ankom | Waiting on new tubing.
12 | With Lab | Taurine - New method | GB Project
13 | With Lab | Vitamin A&E for GB | GB Project
14 | With Lab | Vitamin B1 - Method Set Up | GB Project
15 | With Lab | Vitamin B2 - Method Set Up | GB Project
16 | With Lab | Vitamin B3 for GB | GB Project
17 | With Lab | Vitamin B6 - Method Set Up | GB Project
18 | With Lab | Vitamin C - Method Set Up | Waiting for fluorimeter.
19 | With Quality | ANOX Consolidation | Read & Understand stage
20 | With Quality | Iodine by GB Method | John Speers to do. Waiting on reagents.
21 | With IT | Available CHO
22 | With IT | B Group move to UPLC | Low priority due to GB
23 | With IT | CODEX Variation to PROT01
24 | With IT | Energy Calculation inc acetic acid
25 | With IT | Moisture Consolidation
26 | To Do | FAME Consolidation | FAME04 > FAME02, low priority
27 | To Do | FLOD Consolidation
28 | To Do | Nucleotide retention time shift
29 | To Do | Pesticide C6 Screen
30 | To Do | Validate CAPS01 | Referenence from McCormicks? CS chasing.
31 | To Do | Vitamin B12 - CN extraction - base levels
32 | To Do | Water Activity - linearity check | CAPEX done.
33 | To Do | WHPN Consolidation
34