## List
key | Area | Project | Comment | GB | Project_No | CC | NM | EM | Story
1 | Doing | Cholesterol via GC/MS | Results not stable - to discuss with Trevor. |  | 210 |  | 17005
1 | Doing | Nominate C6 Preferred List | Circulated for comment. |  | 212
2 | With Lab | ASE Trial Extractions | Waiting for filters |  |  | 144
2 | With Lab | Bromide in Mercury Method | Lab trialling need for Br | GB
2 | With Lab | CARN01 Validation Report | Waiting on bias data | GB | 230 |  |  | 17077
2 | With Lab | FAME01 - Trialling KOH | In progress | GB
2 | With Lab | Glycerol Bath | CAPEX done |  | 218
2 | With Lab | MICP02 convert ICPM06 | IT issues?? |  | 216
2 | With Lab | Nitrogen By HACH | In progress |  | 202
2 | With Lab | PVAL and Light Effects | Report created - no feedback yet. |  | 203
2 | With Lab | RMDX using Ankom | Waiting on new tubing.
2 | With Lab | Taurine - New method | GB Project | GB | 226
2 | With Lab | Vitamin A&E for GB | GB Project | GB | 225 |  | 17011
2 | With Lab | Vitamin B1 - Method Set Up | GB Project | GB | 223 |  | 17009
2 | With Lab | Vitamin B2 - Method Set Up | GB Project | GB | 234 |  | 17012
2 | With Lab | Vitamin B3 for GB | GB Project | GB | 235 |  | 17014
2 | With Lab | Vitamin B6 - Method Set Up | GB Project | GB | 224 |  | 17010
2 | With Lab | Vitamin C - Method Set Up | Waiting for fluorimeter. | GB | 222 |  | 17008
3 | With Quality | ANOX Consolidation | Read & Understand stage |  | 155 | 137
3 | With Quality | Iodine by GB Method | John Speers to do. Waiting on reagents. | GB | 236 |  | 17015
4 | With IT | Available CHO |  |  | 198
4 | With IT | B Group move to UPLC | Low priority due to GB |  | 137
4 | With IT | CODEX Variation to PROT01
4 | With IT | Energy Calculation inc acetic acid | [6 empty] | 255
4 | With IT | Moisture Consolidation |  |  | 197
6 | To Do | FAME Consolidation | FAME04 > FAME02, low priority |  |  | 149
6 | To Do | FLOD Consolidation |  |  | 214 | 154
6 | To Do | Nucleotide retention time shift
6 | To Do | Pesticide C6 Screen |  |  | 212
6 | To Do | Validate CAPS01 | Referenence from McCormicks? CS chasing. |  | 204
6 | To Do | Vitamin B12 - CN extraction - base levels |  | GB
6 | To Do | Water Activity - linearity check | CAPEX done.
6 | To Do | WHPN Consolidation
7 | Done | ASHS02 - GB alterations |  | GB
7 | Done | Autotitrator CC to complete
7 | Done | CHLN01 Validation Report |  | GB | 229 |  |  | 17078
7 | Done | FAME02 MU Calculations
7 | Done | Lactoferrin method (TMI) |  | GB | 217 |  | 17004
7 | Done | Len's Milk Complaint Sample
7 | Done | MG GB File - update to per 100g
7 | Done | MU Discussion Paper for MG
7 | Done | Nucleotides - AQ transfer
7 | Done | Protocols for GB Validations
7 | Done | Review GB 'Identicals'
7 | Done | SUGA03 to inc GB extraction
7 | Done | SUGA09 - Low Lactose | Active |  | 213
7 | Done | TITA14 Nested testing - Wendy
7 | Done | TITA14 Validation Report |  | GB | 228
7 | Done | VIK101 - NATA Validation |  | GB | 231